## Slide 1: CCAMP-55
WG Document Status
Nov 18, 2002

## Slide 2: Shipped!
Base documents for generalized signaling
  draft-ietf-mpls-generalized-signaling-09.txt
  draft-ietf-mpls-generalized-cr-ldp-07.txt
  draft-ietf-mpls-generalized-rsvp-te-09.txt
Many thanks to the Editor, Authors, um, Contributors, ADs, RFC Editors and IANA!
First RFCs to come out of CCAMP WG (jointly with MPLS WG)

## Slide 3: Shipping …
LMP base spec
  draft-ietf-ccamp-lmp-07.txt
Final WG Last Call finished Oct 1, ‘02
Two comments raised and addressed
New version (-07) out
En route to IESG

## Slide 4: Fell Through the Cracks
SONET/SDH Extensions
  draft-ietf-ccamp-gmpls-sonet-sdh-07.txt
  New version posted, all issues closed
  Will send to IESG
Architecture
  draft-ietf-ccamp-gmpls-architecture-03.txt
  Verify that it’s up-to-date, then send to IESG

## Slide 5: Packed and Ready to Go
Routing extensions for GMPLS
  draft-ietf-ccamp-gmpls-routing-05.txt
  draft-ietf-ccamp-ospf-gmpls-extensions-08
Final WG Last Call ended Aug 28, ‘02
  No public comments received
These will be checked for nits, then sent to the IESG

## Slide 6: Informationals
GMPLS Framework for SONET/SDH
  draft-ietf-ccamp-sdhsonet-control-01.txt
  Consensus to ship to the IESG?
Signaling non-standard SONET/SDH features
  draft-ietf-ccamp-gmpls-sonet-sdh-extensions-03.txt
  Technical work done, still needs some editorial fixes of nits

## Slide 7: On the Way
SONET/SDH LMP Test Messages
  draft-ietf-ccamp-lmp-test-sonet-sdh-00.txt
  Check with ITU/T1.X1
  Consensus to send this to the IESG?
GMPLS implementation survey
  draft-ietf-ccamp-gmpls-signaling-survey-03.txt
  Forwarded to IETF secretary as an Implementation Report

## Slide 8: In Progress …
LMP-DWDM
Signaling for G.709
GMPLS MIBs
LMP MIB

## Slide 9: Myriads of Other Docs
If you want your document discussed during a CCAMP WG meeting
  please send WG chairs email saying how the document fits into CCAMP charter (call out explicit work items)
  Please begin a discussion of your doc on the mailing list so that you can discuss (not present) your document